## Data Integration (ETL)
Section ID | Section Name | Estimated Time
1 | Employee Table | 10
2 | Employee Table (Advanced Analytics - Attrition Prediction) | 15
3 | Recruitment Table | 7
4 | Leave Table | 5
5 | Training Table | 3
6 | Engagement Table | 7
7 | Engagement Table (Advanced Analytics - Sentiment Analysis) | 10
8 | Data Dictionary | 0

## DAX Measurements and Visualizat
Page ID | Category Name | Page Name | Section IDs | Estimated Time
1 | 1. Executive Insights | HR at a Glance | 1,4 | 3
2 | 1. Executive Insights | Exec Dashboard | 1,4 | 3
3 | 1. Executive Insights | Top 10 Questions | 1,3,4,5 | 4
4 | 1. Executive Insights | Cost Distribution | 1 | 5
5 | 1. Executive Insights | Scorecards 1 | 1,3,5 | 2
6 | 1. Executive Insights | Scorecards 2 | 1,4 | 3
7 | 1. Executive Insights | Hires 4 Boxes | 1 | 3
8 | 1. Executive Insights | Leavers 4 Boxes | 1 | 3
9 | 2. Recruitment | Recruitment | 3 | 3
10 | 2. Recruitment | Recruitment Status | 3 | 3
11 | 2. Recruitment | Recruitment by Gender | 3 | 2
12 | 2. Recruitment | Recruitment by Job Level | 3 | 3
13 | 2. Recruitment | Time to Offer/Hire | 3 | 3
14 | 3. Hires | New Starters | 1 | 3
15 | 3. Hires | New Starters by Gender | 1 | 2
16 | 3. Hires | New Starters by Job Level | 1 | 2
17 | 4. Diversity & Inclusion | Diversity Analysis | 1 | 3
18 | 4. Diversity & Inclusion | Demographic Analysis | 1 | 3
19 | 4. Diversity & Inclusion | Organization Level | 1 | 2
20 | 4. Diversity & Inclusion | Workforce Flow | 1 | 5
21 | 5. Salary | Salary Analysis (Avg) | 1 | 3
22 | 5. Salary | Salary Analysis (Total) | 1 | 3
23 | 5. Salary | Pay Gap Index | 1 | 2
24 | 5. Salary | Pay Gap Amount | 1 | 2
25 | 5. Salary | Pay Gap by Business Unit | 1 | 2
26 | 5. Salary | Pay Gap by Org Level | 1 | 3
27 | 5. Salary | Correlation & Prediction | 1 | 2
28 | 5. Salary | Pay Gap What-if | 1 | 3
29 | 6. Survey Analysis | Insights | 6 | 2
30 | 6. Survey Analysis | Analysis by Parameters | 6 | 1
31 | 6. Survey Analysis | Analysis by Questions | 6 | 2
32 | 6. Survey Analysis | Leadership Index | 6 | 1
33 | 6. Survey Analysis | Performance Management | 6 | 1
34 | 6. Survey Analysis | Correlation Analysis | 6 | 2
35 | 6. Survey Analysis | Survey Insights | 6 | 1
36 | 6. HR Profile & Trends | Headcount | 1 | 2
37 | 6. HR Profile & Trends | Employee Profile | 1,4,5 | 2
38 | 6. HR Profile & Trends | Historical & Trends | 1 | 1
39 | 6. HR Profile & Trends | Span of Control | 1 | 3
40 | 6. HR Profile & Trends | Departmental Dashboards | 1 | 3
41 | 6. HR Profile & Trends | Departmental Dashboards | 4 | 3
42 | 6. HR Profile & Trends | Departmental Dashboards | 4 | 3
43 | 6. HR Profile & Trends | Departmental Dashboards | 1 | 3
44 | 6. HR Profile & Trends | Departmental Dashboards | 1 | 3
45 | 7. Performance & Training | Performance Rating | 1 | 3
46 | 7. Performance & Training | Nine Box Performance Grid | 1 | 4
47 | 7. Performance & Training | Training Analysis | 5 | 2
48 | 8. Leave & Availability | Leave Taken | 4 | 3
49 | 8. Leave & Availability | Leave Balance | 4 | 3
50 | 8. Leave & Availability | Leave Liability | 4 | 2
51 | 8. Leave & Availability | Absenteeism | 4 | 3
52 | 8. Leave & Availability | Availability | 4 | 2
53 | 9. Terminations | Termination Profile | 1 | 3
54 | 9. Terminations | Termination Analysis | 1 | 2
55 | 9. Terminations | Attrition Analysis | 1 | 3
56 | 9. Terminations | Attrition Prediction | 2 | 20
57 | 9. Terminations | Great Resignation | 1 | 2
58 | 10. Data Governance | HR Dictionary | 8 | 2
59 | 10. Data Governance | Data Quality | 1 | 5
60 | 10. Data Governance | Data Validation | 1 | 4

## Project Deployment
Dev ID | Dev Name | Estimated Time
1 | Project Management (Project Manager time) | 20
2 | Weekly meetings (standups & Showcases), managing technical development tasks in Kanban Board (Planner), and answering comments by the developer | 20
3 | Updating dashboard according to the comments/feedback from business after the UAT (user acceptance test) is done | 10
4 | Adding new Slicers to the reports (up to 3 new slicers) | 7
5 | Setting up automation | 2
6 | Setting up Security Levels (Row-level & Object Level Security) | 4
7 | Setting up page-level security | 8
8 | Running Performance Checks (DAX & Visuals) | 4
9 | Providing the list of all measures in the HR dashboard | 1
10 | Providing the documentation of the available and delivered reports | 2
11 | GitHub Integration | 2
12 | Moving the dashboard into the PROD workspace and set up Apps if Required | 3
13 | Providing Usage Metrics Report for the HR Dashboard in Power BI Service | 2
14 | Running Knowledge Transfer (Training) sessions for the end users | 2

## Project Managers
Project Manager ID | Project Manager Name | Salary Rate per Hour
1 | Person 1 | 100
2 | Person 2 | 150
3 | Person 3 | 200

## Developers
Developer ID | Developer Name | Salary Rate per Hour
1 | Developer 1 | 100
2 | Developer 2 | 150
3 | Developer 3 | 200